## Timeline
Date | Group | Planning Action | Research and Data Action | Budget Prep Action
December 2016 | PRIEC/SE/SSSP/BSI | Alignment of Goals Framework: IEPI, Strategic Plan (EMP), Student Equity, Student Success, Basic Skills | Update alignment of indicators and metrics to track progress towards goals
January 2017 | PRIEC | Information and Discussion
January 2017 | Vice Chancellor of Finance | Projected funds for 2017-2018 fiscal year based on Governor’s budget proposal reviewed with the PBIC & Chancellor’s Cabinet
January 2017 | Chancellor and Cabinet | Chancellor & Cabinet make final decision regarding allocation of new faculty hires & recruitment process for hiring new faculty begins
January & February 2017 |  | Prioritized program review resource requests ranked and shared with participatory governance committees |  | PBC feedback to colleges; Gov. budget released
February 2017 | Vice Chancellor of Finance | Projected funds for following fiscal year and tentative distribution to campuses |  | Campus budget processes determine priorities, allocate of fund, & prepare budget forms for submission to District Finance Office
February 2017 | PRIEC | Recommend assessment rubric for Institutional Learning Outcomes (every 3 years, 2015 last)
February 2017 | PRIEC | Review Fall Institutional Effectiveness Survey results | Summarize survey results | Budget instructions submitted to campuses
February-March 2017 |  | Initiate CCSSE and CECE surveys (every two years) | Prepare data files; establish samples; administer surveys
February-March 2017 | Various committees | Vet & approve ranked resource requests
March 2017 | PRIEC | Review of ACCJC Annual Report | Prepare data for ACCJC Annual Report | Departments begin to plan for future budget
March 2017 | PRIEC | Initiate Annual Goal Setting Discussions |  | Campus prepares budget submission to District
March/April 2017 | Office of R & P | Employee Voice Survey | Dean of R&P administers survey | Submit prioritized lists of new resources (other than faculty) to the DTC and DFC
April 2017 | Academic Senate | Information |  | Campus submits budget to District (prelim)
April 2017 | College Council | Adopts rubric and assessment for Institutional Learning Outcomes (every 3 years)
April/May 2017 | PRIEC/DAS/College Council | Collaboratively Establish Goals
April/May 2017 | All Partic. Gov. Committees | Committee Self-Evaluations
May 2017 | Academic Senate | Review Goals
May 2017 | President | Chancellor’s Cabinet updated on status of preliminary budget. Review, discuss, and recommend adjustments brought forth
June (early) 2017 | Peralta Board of Trustees | Approval of Goals |  | Tentative budget to Board of Trustees
June 15, 2017 | Office of R & P | Submit IEPI Goals to CCCCO
July 2017 |  | Admin. Offices prepare program review/unit plan templates | Prep program/unit level data for dissemination to departments by Flex Day. Offer Program Review and APU flex training with their data.
August 2017 | PRIEC/Academic Senate/College Council/(Flex?) | President presents college with strategic goals and institutional guidelines for the planning year | President, VP's, Dean of R&P and DBS provide flex day present Program Review/APU templates and processes
September 2017 | Office of R & P |  | Delivery of Institutional Data to departments to initiate annual program updates/program reviews - pre-populate the forms if possible
September 2017 | Board of Trustees |  |  | Final approval of FY budget by BOT
September 2017 | College President | College follow-up accreditation reports to BOT for discussion & review
October 2017 | All | Annual program reviews and/or unit plans are due
October 2017 |  | Departmental resource requests are due
October 2017 | PRIEC | Discuss Institutional Learning Outcomes (every 3 years)
October 2017 | College Council | Affirms Institutional Learning Outcomes (every 3 years)
October and November | VPSS, VPI, Deans | Convene work groups to validate program reviews for completion
November 2017 | Deans | Deans review/prioritize/recommend resource requests
November 2017 | VPs/President | Senior management compiles resource requests from deans and other administrative areas
November 2017 | Various committees | Provide overview of Planning & Budget Timeline, Budget Development and PIO/AUO processes to colleges/community |  | CoA Director of Business Services
November 2017 | Office of R & P | SURVEY: Institutional Effectivness | Dean of R&P administers survey
December 2017 | Academic Senate, Classified Senate, Budget Committee, ASCOA, Department Chairs, Student Services Council | Resource requests are routed through participatory governance groups
December 2017 | College Council | Resource requests are forwarded to College Council which reviews and recommends resource requests to the College President
December 2017 | President's Office | Resource requests are synthesized and summary is distributed to campus
December 2017 | DTC, DFC, DEC, PBC | Resource requests are submitted to District Participatory Governance Groups
SURVEYS
Institutional Effectiveness Survey | Late Fall | Bring to PRIEC in Feb for them to review….give them the last 3 years of data and get feedback | Dean of R&P administers survey
CECE | Feb/March |  | Dean of R&P administers survey
CCSSE | Feb/March |  | Dean of R&P administers survey
Employee Voice | Spring | It was too long *cribbed from Skyline. Shorten and refine it. Do it again….in the Spring | Dean of R&P administers survey
Survey | Late Fall | Dept Chairs debrief how program review went
Survey | Late Fall | Assess program review/APU validation process
ASSESSMENTS
Student Learning Outcomes | Annual
Program Learning Outcomes | Annual
Service Area Outcomes | Annual
Institutional Learning Outcomes | Annual

## Sheet1
Date | Action Item | Responsible Party
2016-07-01 | Compile unit plan/program review templates with student data | Support staff, VPI, VPSS, DBS
August 2016 – Campus professional day | Roll out Program Review/APU templates | VPI, President, VPSS, DBS, support staff
2016-09-01 | Fiscal year 2016-2017 Final Budget approved by BOT | Vice Chancellor of Finance & Administration
2016-09-01 | College follow-up accreditation reports to BOT for discussion & review | President
Mid-October 2016 | Program Reviews/Unit Plans due | All College
October & November 2016 | Convene work groups to validate program reviews for completion | Instructional groups, student service groups, administrative groups
2016-11-01 | Update campus budget calendar based upon district board approved planning calendar | DBS – Approved by Budget
2016-11-01 | Integrated Planning Budget Development Calendar presented to BOT for adoption | VC Finance & Administration
2016-11-01 | Provide overview of Planning & Budget Timeline, Budget Development and PIO/AUO processes to colleges/community | Budget Director
2016-11-01 | Recommendations of BAM Task Force shared with PBC for consideration | BAM TF/PBC
2016-12-01 | Colleges & District Office divisions complete program reviews and program improvement objectives/resource requests by January 30, 2017& submit faculty hiring lists to DEC & PBC | President or designee
2017-01-01 | Work groups prioritized program review resource requests ranked | Instructional groups, student service groups, administrative groups
January & February 2017 | Prioritized resource requests forwarded to shared governance groups | Instructional groups, student service groups, administrative groups
2017-01-01 | Projected funds for 2017-2018 fiscal year based on Governor’s budget proposal reviewed with the PBIC & Chancellor’s Cabinet | VC Finance & Administration
2017-01-01 | Chancellor & Cabinet make final decision regarding allocation of new faculty hires & recruitment process for hiring new faculty begins | Chancellor, Cabinet
2017-02-01 | Projected funds for 2017-2018 fiscal year and tentative distribution to campuses | VC Finance & Administration
2017-02-01 | Prior & current year line item budgets, instruction packets, and due dates distributed to President & Chancellor for distribution to managers with budget authority | Chancellor, Finance Office, Presidents
February to April 2017 | Campus budget processes determine priorities, allocate of fund, & prepare budget forms for submission to District Finance Office | President, VPI, VPSS, DBS, managers, campus staff
2017-02-01 | Vet & approve ranked resource requests | Shared governance groups
2017-03-01 | Submit prioritized lists of new resources (other than faculty) to the DTC and DFC | President or designee
2017-03-01 | DTC and DFC send recommendations about prioritized resource lists to PBC | DTC DFC
2017-03-01 | Budget and staffing worksheets are distributed to campuses | Budget Director, VC Finance
2017-04-01 | PBC reviews prioritized resource lists & submits recommendations to the Chancellor &/or Resource allocation committee | PBC
2017-04-01 | Cabinet & Resource allocation committee reviews all resource requests that are not under the purview of a PBIM | Cabinet, RAC
2017-04-01 | Preliminary budget worksheets, including staffing, due to District Finance Office | DBS, finance staff, all responsible budget managers
2017-04-01 | Cabinet and/or RAC makes final recommendations about allocation of new resources to the colleges & District Service Center | Cabinet, RAC
2017-05-01 | Governor releases the may Budget revision | Governor
2017-05-01 | Chancellor’s Cabinet updated on status of preliminary budget. Review, discuss, and recommend adjustments brought forth | President
2017-05-01 | Chancellor and Cabinet review PBC & RAC recommendations and reconcile against the May Budget Revision | Chancellor, Cabinet
2017-05-01 | Draft tentative budget submitted to the Chancellor | Vice Chancellor for Finance & Administration
2017-06-01 | Tentative 2017-2018 Budget is presented to the BOT for discussion & review | Vice Chancellor for Finance & Administration